## Plan-Fact
@stsgs/ui -- Extraction Checklist: Plan vs Fact
Updated: 13.05.2026 ¦ Anti-monolith: <=150 lines, <=3 useState, forwardRef, JSDoc, data-slot
Source | Repository | Files | Plan Extract | Plan Skip | Plan Dup | Fact Extract | Fact Skip | Fact Dup | Completion | Notes
Ormuz-monitor | stsgs1980/Ormuz-monitor | 2000 | 74 | 0 | 0 | 74 | 0 | 0 |  | Full extraction of all Scifi components
Code-Realm | stsgs1980/Code-Realm | 24 | 12 | 8 | 4 | 12 | 8 | 4 |  | FloatingDecorations, CodeBlock, SliderControl + 5 hooks
Component-Browser | stsgs1980/Component-Browser | 11 | 6 | 1 | 4 | 6 | 1 | 4 |  | 3 remaining from plan + ForceGraph verified
Z.Code-Guide | stsgs1980/Z.Code-Guide-Coding-Tool-Helper | 71 | 8 | 55 | 8 | 8 | 55 | 8 |  | 3->8 EXTRACT after removing OKLCH skip argument
TOTAL

## Components
@stsgs/ui -- Full Component List
Plan = decision from analysis doc. Fact = actual status after extraction.
# | Source | Component | Layer | Plan | Fact | Files | Description
1 | Ormuz-monitor | TypingEffect | Tier 1 | EXTRACT | DONE | 1 | Typing text effect
2 | Ormuz-monitor | ScifiButton | Tier 1 | EXTRACT | DONE | 1 | Sci-fi button
3 | Ormuz-monitor | ScifiCard | Tier 1 | EXTRACT | DONE | 1 | Sci-fi card
4 | Ormuz-monitor | ScifiInput | Tier 1 | EXTRACT | DONE | 1 | Sci-fi input field
5 | Ormuz-monitor | ScifiToggle | Tier 1 | EXTRACT | DONE | 1 | Sci-fi toggle switch
6 | Ormuz-monitor | ScifiTooltip | Tier 1 | EXTRACT | DONE | 1 | Sci-fi tooltip
7 | Ormuz-monitor | ScifiModal | Tier 1 | EXTRACT | DONE | 1 | Sci-fi modal dialog
8 | Ormuz-monitor | ScifiBadge | Primitive | EXTRACT | DONE | 2 | Badge with variants (sm/md/lg, presets)
9 | Ormuz-monitor | ScifiGauge | Primitive | EXTRACT | DONE | 6 | Ring/arc/linear/segmented gauge
10 | Ormuz-monitor | ScifiCanvasChart | Primitive | EXTRACT | DONE | 8 | Line/bar/area/multi-line chart
11 | Ormuz-monitor | HudCard | Tier 1 | EXTRACT | DONE | 1 | HUD card with accent border
12 | Ormuz-monitor | ScifiSectionHeader | Tier 1 | EXTRACT | DONE | 1 | Sci-fi section header
13 | Ormuz-monitor | AnimatedCounter | Tier 1 | EXTRACT | DONE | 1 | rAF number animation
14 | Ormuz-monitor | MiniSparkline | Tier 1 | EXTRACT | DONE | 1 | Mini sparkline (SVG path)
15 | Ormuz-monitor | ScifiScrollProgress | Tier 1 | EXTRACT | DONE | 1 | Sci-fi scroll progress bar
16 | Ormuz-monitor | BackToTop | Tier 1 | EXTRACT | DONE | 1 | Back to top button
17 | Ormuz-monitor | ScifiButtonGroup | Tier 2 | EXTRACT | DONE | 1 | Button group with variants
18 | Ormuz-monitor | ScifiTabbedView | Tier 2 | EXTRACT | DONE | 1 | Tabs with animated indicator
19 | Ormuz-monitor | ScifiTimeline | Pattern | EXTRACT | DONE | 1 | Event timeline
20 | Ormuz-monitor | ScifiCorrelationGrid | Pattern | EXTRACT | DONE | 3 | Correlation matrix + performance bars
21 | Ormuz-monitor | ScifiScenarioCards | Pattern | EXTRACT | DONE | 1 | Scenario cards (severity)
22 | Ormuz-monitor | ScifiTickerBar | Pattern | EXTRACT | DONE | 1 | Ticker bar (scrolling items)
23 | Ormuz-monitor | ScifiLiveFeed | Pattern | EXTRACT | DONE | 1 | Live event feed
24 | Ormuz-monitor | ScifiRouteTable | Pattern | EXTRACT | DONE | 1 | Route table with risk levels
25 | Ormuz-monitor | ScifiComparisonGrid | Pattern | EXTRACT | DONE | 3 | Comparison grid (spread bars)
26 | Ormuz-monitor | ScifiActorGrid | Pattern | EXTRACT | DONE | 2 | Actor grid + timeline panel
27 | Ormuz-monitor | ScifiCtaSection | Batch 1 | EXTRACT | DONE | 1 | CTA section with metrics
28 | Ormuz-monitor | ScifiEventCalendar | Batch 1 | EXTRACT | DONE | 1 | Event calendar (categories)
29 | Ormuz-monitor | ScifiTransitOverview | Batch 1 | EXTRACT | DONE | 1 | Transit overview (exporters)
30 | Ormuz-monitor | ScifiScenarioAnalysis | Batch 1 | EXTRACT | DONE | 1 | Scenario analysis (factors)
31 | Ormuz-monitor | ScifiImpactBeneficiaries | Batch 1 | EXTRACT | DONE | 1 | Impact beneficiaries
32 | Ormuz-monitor | ScifiNavBar | Batch 1 | EXTRACT | DONE | 2 | Sci-fi navbar (desktop + mobile)
33 | Ormuz-monitor | ScifiHero | Batch 2 | EXTRACT | DONE | 3 | Hero section (particles + radar)
34 | Ormuz-monitor | ScifiLoadingScreen | Batch 2 | EXTRACT | DONE | 3 | Loading screen (hex + stream)
35 | Ormuz-monitor | ScifiAlertPanel | Batch 2 | EXTRACT | DONE | 2 | Alert panel (rows)
36 | Ormuz-monitor | ScifiAlertDashboard | Batch 2 | EXTRACT | DONE | 3 | Alert dashboard (gauge + stats)
37 | Ormuz-monitor | ScifiNewsFeed | Batch 2 | EXTRACT | DONE | 2 | News feed (threat gauge)
38 | Ormuz-monitor | ScifiChartGrid | Batch 2 | EXTRACT | DONE | 2 | Chart grid (card + chart)
39 | Ormuz-monitor | ScifiRiskMatrix | Batch 3 | EXTRACT | DONE | 3 | Risk matrix (grid + details)
40 | Ormuz-monitor | ScifiAssetHeatmap | Batch 3 | EXTRACT | DONE | 3 | Asset heatmap
41 | Ormuz-monitor | ScifiPulseMeter | Batch 3 | EXTRACT | DONE | 3 | Pulse meter (rings + bars)
42 | Ormuz-monitor | ScifiSentimentGauge | Batch 3 | EXTRACT | DONE | 3 | Sentiment gauge (main + mini)
43 | Ormuz-monitor | ScifiTensionIndex | Batch 3 | EXTRACT | DONE | 3 | Tension index (gauge + sparkline)
44 | Ormuz-monitor | ScifiCorrelationTable | Batch 3 | EXTRACT | DONE | 3 | Correlation table (sparkline)
45 | Ormuz-monitor | ScifiCostCalculator | Batch 6B | EXTRACT | DONE | 3 | Cost calculator (slider + select)
46 | Ormuz-monitor | ScifiRegionMap | Batch 6B | EXTRACT | DONE | 3 | Region map (SVG + details)
47 | Ormuz-monitor | ScifiGlobeView | Batch 6B | EXTRACT | DONE | 7 | 3D globe (Three.js + overlays)
48 | Ormuz-monitor | ScifiReserveMonitor | Batch 6B | EXTRACT | DONE | 3 | Reserve monitor (gauge + sparkline)
49 | Ormuz-monitor | ScifiScenarioEngine | Batch 6B | EXTRACT | DONE | 3 | Scenario engine (factors + score)
50 | Ormuz-monitor | ScifiAssetTracker | Batch 7 | EXTRACT | DONE | 1 | Asset tracker
51 | Ormuz-monitor | ScifiChainTracker | Batch 7 | EXTRACT | DONE | 1 | Chain tracker
52 | Ormuz-monitor | ScifiComplianceTracker | Batch 7 | EXTRACT | DONE | 4 | Compliance tracker (gauge + rows)
53 | Ormuz-monitor | ScifiDemandCurve | Batch 7 | EXTRACT | DONE | 3 | Demand curve (chart + impact)
54 | Ormuz-monitor | ScifiDisruptionPanel | Batch 7 | EXTRACT | DONE | 1 | Disruption panel
55 | Ormuz-monitor | ScifiEnergyDashboard | Batch 7 | EXTRACT | DONE | 3 | Energy dashboard
56 | Ormuz-monitor | ScifiEnvironmentalImpact | Batch 7 | EXTRACT | DONE | 4 | Environmental impact
57 | Ormuz-monitor | ScifiFleetMonitor | Batch 7 | EXTRACT | DONE | 1 | Fleet monitor
58 | Ormuz-monitor | ScifiFlowTracker | Batch 7 | EXTRACT | DONE | 1 | Flow tracker
59 | Ormuz-monitor | ScifiForecastPanel | Batch 7 | EXTRACT | DONE | 5 | Forecast panel (curve + signal)
60 | Ormuz-monitor | ScifiIndicatorPanel | Batch 7 | EXTRACT | DONE | 7 | Indicator panel (RSI/MACD/Boll)
61 | Ormuz-monitor | ScifiInfrastructureMap | Batch 7 | EXTRACT | DONE | 4 | Infrastructure map
62 | Ormuz-monitor | ScifiLevelAnalysis | Batch 7 | EXTRACT | DONE | 3 | Level analysis (chart + cards)
63 | Ormuz-monitor | ScifiProcessingPanel | Batch 7 | EXTRACT | DONE | 6 | Processing panel (charts)
64 | Ormuz-monitor | ScifiSankeyFlow | Batch 7 | EXTRACT | DONE | 2 | Sankey diagram (bezier paths)
65 | Ormuz-monitor | ScifiStatsSection | Batch 7 | EXTRACT | DONE | 1 | Stats section
66 | Ormuz-monitor | ScifiTransitMonitor | Batch 7 | EXTRACT | DONE | 1 | Transit monitor
67 | Ormuz-monitor | ScifiPeriodSelector | Batch 7 | EXTRACT | DONE | 1 | Period selector
68 | Ormuz-monitor | ScifiCorrelationDashboard | Batch 7 | EXTRACT | DONE | 5 | Correlation dashboard
69 | Ormuz-monitor | ScifiVersusPanel | Batch 8 | EXTRACT | DONE | 3 | VS panel (bar + team cards)
70 | Ormuz-monitor | ScifiTrackedAssets | Batch 8 | EXTRACT | DONE | 3 | Tracked assets
71 | Ormuz-monitor | ScifiTacticalMap | Batch 8 | EXTRACT | DONE | 2 | Tactical map (markers + labels)
72 | Code-Realm | use-mounted | hook | EXTRACT | DONE | 1 | SSR-safe mount
73 | Code-Realm | use-copy-to-clipboard | hook | EXTRACT | DONE | 1 | Clipboard API + fallback
74 | Code-Realm | use-animated-counter | hook | EXTRACT | DONE | 1 | rAF number animation
75 | Code-Realm | use-scroll-progress | hook | EXTRACT | DONE | 1 | 0-100% scroll progress
76 | Code-Realm | use-local-storage | hook | EXTRACT | DONE | 1 | Reactive localStorage
77 | Code-Realm | slider-control | ui | EXTRACT | DONE | 1 | Labeled range slider
78 | Code-Realm | color-picker-input | ui | EXTRACT | DONE | 1 | Native picker + hex + presets
79 | Code-Realm | copy-button | ui | EXTRACT | DONE | 1 | Copy with check feedback
80 | Code-Realm | code-block | ui | EXTRACT | DONE | 1 | VS Code chrome + line numbers
81 | Code-Realm | floating-decorations | feature | EXTRACT | DONE | 1 | CSS-only floating symbols
82 | Code-Realm | scroll-progress-bar | feature | EXTRACT | DONE | 1 | Fixed scroll progress
83 | Code-Realm | activity-timeline | feature | EXTRACT | DONE | 1 | Vertical timeline
84 | Code-Realm | ToggleGroup | ui | SKIP | SKIP | 0 | Already in UI-Kit (shadcn)
85 | Code-Realm | SectionShell | feature | SKIP | SKIP | 0 | Too project-specific
86 | Code-Realm | GradientGenerator | section | SKIP | SKIP | 0 | Domain generator
87 | Code-Realm | ShadowGenerator | section | SKIP | SKIP | 0 | Domain generator
88 | Code-Realm | JsonFormatter | section | SKIP | SKIP | 0 | Domain tool
89 | Code-Realm | PaletteGenerator | section | SKIP | SKIP | 0 | Domain generator
90 | Code-Realm | TypographyTool | section | SKIP | SKIP | 0 | Domain tool
91 | Code-Realm | GlitchEffect | section | SKIP | SKIP | 0 | Domain effect
92 | Component-Browser | ForceGraph | ui | EXTRACT | DONE | 6 | SVG force graph (physics)
93 | Component-Browser | use-keyboard-shortcuts | hook | EXTRACT | DONE | 1 | ShortcutMap + ctrl/meta parsing
94 | Component-Browser | CompareModal | feature | EXTRACT | DONE | 5 | Modal: cards + bar + diff
95 | Component-Browser | StatsDashboard | feature | EXTRACT | DONE | 5 | Dashboard: cards + donut
96 | Component-Browser | search-panel | feature | DUPLICATE | DUPLICATE | 0 | Already command-palette
97 | Component-Browser | ModelCard | feature | SKIP | SKIP | 0 | Tied to GLMModel type
98 | Component-Browser | CompareSlider | feature | ORIGINAL | DONE | 3 | Created from scratch
99 | Z.Code-Guide | use-active-section | hook | EXTRACT | DONE | 2 | IntersectionObserver active section
100 | Z.Code-Guide | section-header | ui | EXTRACT | DONE | 2 | Numbered heading + animate
101 | Z.Code-Guide | status-dot | ui | EXTRACT | DONE | 2 | Status indicator (4 variants)
102 | Z.Code-Guide | mobile-page-header | feature | EXTRACT | DONE | 2 | Sticky mobile header
103 | Z.Code-Guide | icon-sidebar-nav | feature | EXTRACT | DONE | 2 | Vertical icon nav + active bar
104 | Z.Code-Guide | keyboard-shortcuts-grid | feature | EXTRACT | DONE | 2 | Dual-platform kbd grid
105 | Z.Code-Guide | pipeline-stepper | feature | EXTRACT | DONE | 3 | Responsive horiz/vert stepper
106 | Z.Code-Guide | version-history | feature | EXTRACT | DONE | 3 | Version timeline + pill strip
107 | Z.Code-Guide | CopyButton | ui | DUPLICATE | DUPLICATE | 0 | Already copy-button
108 | Z.Code-Guide | CodeBlock | ui | DUPLICATE | DUPLICATE | 0 | Already code-block
109 | Z.Code-Guide | TaxiDivider | ui | DUPLICATE | DUPLICATE | 0 | Already separator
110 | Z.Code-Guide | ReadingProgress | feature | DUPLICATE | DUPLICATE | 0 | Already scroll-progress-bar
111 | Z.Code-Guide | ScrollToTop | feature | DUPLICATE | DUPLICATE | 0 | Already back-to-top
112 | Z.Code-Guide | SearchDialog | feature | DUPLICATE | DUPLICATE | 0 | Already command-palette
113 | Z.Code-Guide | ThemeToggle | feature | DUPLICATE | DUPLICATE | 0 | Already theme-toggle
114 | Z.Code-Guide | Footer | feature | DUPLICATE | DUPLICATE | 0 | Already footer-section
115 | Z.Code-Guide | 13 sections | section | SKIP | SKIP | 0 | Domain sections (QuickStart, Models etc.)
116 | Z.Code-Guide | 8 zcode features | feature | SKIP | SKIP | 0 | Domain zcode features
117 | Z.Code-Guide | MobileMenu | feature | SKIP | SKIP | 0 | Buildable from sheet + nav
118 | Z.Code-Guide | GuideLayout | feature | SKIP | SKIP | 0 | Domain orchestrator
119 | Z.Code-Guide | 2 promo cards | feature | SKIP | SKIP | 0 | Domain promo cards
120 | Z.Code-Guide | 3 hooks | hook | SKIP | SKIP | 0 | useSearch, useTheme, usePageState
121 | Original/shadcn | Layout (51 recipes) | ui | ORIGINAL | DONE | 1 | Grid layout engine
122 | Original/shadcn | Grid/GridItem | ui | ORIGINAL | DONE | 1 | CSS Grid primitives
123 | Original/shadcn | Container | ui | ORIGINAL | DONE | 1 | Max-width wrapper
124 | Original/shadcn | Stack | ui | ORIGINAL | DONE | 1 | Flex stack
125 | Original/shadcn | Cluster | ui | ORIGINAL | DONE | 1 | Wrapping horizontal flex
126 | Original/shadcn | ColumnBrowser | ui | ORIGINAL | DONE | 1 | N-column master-detail
127 | Original/shadcn | SearchableFilterableGrid | ui | ORIGINAL | DONE | 1 | Search + tabs + grid
128 | Original/shadcn | BentoGrid/BentoItem | ui | ORIGINAL | DONE | 1 | Variable-size grid
129 | Original/shadcn | MasonryGrid | ui | ORIGINAL | DONE | 1 | CSS-columns masonry
130 | Original/shadcn | 48 shadcn/ui | ui | CB-EXTRACT | DONE | 48 | button, card, dialog etc.
131 | Original/shadcn | HeroSection | section | ORIGINAL | DONE | 1 | Hero section
132 | Original/shadcn | NavbarSection | section | ORIGINAL | DONE | 1 | Navbar
133 | Original/shadcn | FooterSection | section | ORIGINAL | DONE | 1 | Footer
134 | Original/shadcn | CTABanner | section | ORIGINAL | DONE | 1 | CTA banner
135 | Original/shadcn | StaggeredHero | section | ORIGINAL | DONE | 1 | Staggered hero
136 | Original/shadcn | ThreeColumnBrowser | section | ORIGINAL | DONE | 1 | 3-column browser
137 | Original/shadcn | FourColumnBrowser | section | ORIGINAL | DONE | 1 | 4-column browser
138 | Original/shadcn | FaqSection | section | ORIGINAL | DONE | 1 | FAQ accordion + grid
139 | Original/shadcn | TestimonialsSection | section | ORIGINAL | DONE | 1 | Testimonials
140 | Original/shadcn | StatsSection | section | ORIGINAL | DONE | 1 | Stats row + grid
141 | Original/shadcn | FeaturesSection | section | ORIGINAL | DONE | 1 | Features grid + bento
142 | Original/shadcn | PricingCards | section | ORIGINAL | DONE | 1 | Pricing tiers
143 | Original/shadcn | ContactSection | section | ORIGINAL | DONE | 1 | Contact form
144 | Original/shadcn | LogoCloud | section | ORIGINAL | DONE | 1 | Logo cloud
145 | Original/shadcn | NewsletterSection | section | ORIGINAL | DONE | 1 | Newsletter
146 | Original/shadcn | IdeLayout | feature | ORIGINAL | DONE | 1 | IDE layout
147 | Original/shadcn | ResponsiveShowcase | feature | ORIGINAL | DONE | 1 | Responsive preview
148 | Original/shadcn | CommandPalette | feature | ORIGINAL | DONE | 1 | Command palette
149 | Original/shadcn | ThemeToggle | feature | ORIGINAL | DONE | 1 | Theme toggle
150 | Original/shadcn | SearchPanel | feature | ORIGINAL | DONE | 1 | Search panel
151 | Original/shadcn | CompareSlider | feature | ORIGINAL | DONE | 3 | Before/after slider
152 | Original/shadcn | useBreakpoint | hook | ORIGINAL | DONE | 1 | isMobile/isTablet/isDesktop
153 | Original/shadcn | useLayoutAdvice | hook | ORIGINAL | DONE | 1 | Layout recommendation
| TOTAL |  |  | DONE: 129 ¦ SKIP: 15 ¦ DUP: 9